## Assumptions and Background
Introduction
This tool allows the executive team to gauge whether chosen projects will fit team capacity
It's intended to be used primarily as a rough estimating tool, not as direct resource allocation. Several possible models are provided.
Prerequisites
None. No macros or special add-in functions are used.
You need to gather information and sizing estimates on your proposed projects first
You need to confirm the rough sizing (in hours) for each category of project, and enter this information in the "Estimating Code Values" block
Steps
1) Enter/confirm your assumptions in the assumptions block of the spreadsheet tab you've chosen as your desired model. Green fields need entry.
2) Determine the total number of available headcount in each relevant area and enter that into the green fields
3) Play "what if" with choosing projects, per your other criteria (e.g., ROI, risk, etc.) to make sure the total portfolio does not exceed capacity
Maintenance
This spreadsheet is simply a template, and will require modification for your situation
Weaknesses/Still To Do
Background and Assumptions
See http://www.peterkretzman.com
Creative Commons License
© Copyright 2009-2013 Peter Kretzman.
No support for this model is implied.
This spreadsheet is licensed under a Creative Commons Attribution 3.0 license.
See http://creativecommons.org/licenses/by/3.0/
This kind of license is also referred to as copyleft.

## Simple model
| Estimate | Total Hours for Project | Include in Final Total? | Hours for Final Sum
All Proposed Projects
Project Artichoke | S | 200 | x | 200
Project Banana | M | 700
Project Cauliflower | L | 1500 | x | 1500
| All estimated projects | Included projects
Projects presented & estimated | 3 | 2
Total hours | 2400 | 1700
Total work months | 17.8571 | 12.6488
Total heads needed for period | 5.9524 | 4.2163 | OVER CAPACITY
Heads on hand (approximate) | 4 | 4
Hours available from heads on hand | 1612.8 | 1612.8
Assumptions:
Estimating Code Values
| Code | Work Hrs
| S | 200
| M | 700
| L | 1500
Other Assumptions:
| Productivity % | 80%
| Work hrs/mo | 134.4
| Months/period | 3

## More complex model
| Arch | Dev | QA | Operations | Total Hours for Project | Include in Final Total? | Hours for Final Sum
All Proposed Projects
Project Artichoke | S | M | S | M | 500 | x | 500
Project Banana | M | M | S | M | 650 | x | 650
Project Cauliflower | M | L | L | L | 2600
Project Dillpickle | S | M | S | S | 350 | x | 350
Total hours estimated | 500 | 1400 | 950 | 1250 | 4100 |  | 1500
Total hours included | 300 | 600 | 150 | 450
Total work months included | 2.2321 | 4.4643 | 1.1161 | 3.3482
Total heads needed | 0.74405 | 1.4881 | 0.37202 | 1.1161
Heads on hand (approximate) | 2 | 4 | 3 | 3
| All estimated projects | Included projects
Projects presented & estimated | 4 | 3
Total hours | 4100 | 1500
Total work months | 30.506 | 11.1607
Total heads needed for period | 10.1687 | 3.7202
Heads on hand (approximate) | 12 | 12
Hours available from heads on hand | 4838.4 | 4838.4
Assumptions:
Estimating Code Values
| Code | Work Hrs
| S | 50
| M | 200
| L | 800
Other Assumptions:
| Productivity % | 80%
| Work hrs/mo | 134.4
| Months/period | 3

## Yet more complex model
| Arch | UI design | Dev | QA | Operations | Total Hours for Project | Include in Final Total? | Hours for Final Sum
All Proposed Projects
Project Artichoke | 4 | 2 | 3 | 5 | 4 | 2100 | x | 2100
Project Banana | 2 | 3 | 4 | 3 | 2 | 1200 | x | 1200
Project Cauliflower | 2 | 3 | 3 | 3 | 2 | 950
Project Dillpickle | 2 | 3 | 4 | 3 | 2 | 1200 | x | 1200
Total hours estimated | 800 | 850 | 1500 | 1500 | 800 | 5450 |  | 4500
Total hours included | 700 | 600 | 1250 | 1250 | 700
Total work months included | 5.2083 | 4.4643 | 9.3006 | 9.3006 | 5.2083
Total heads needed | 1.7361 | 1.4881 | 3.1002 | 3.1002 | 1.7361
Heads on hand (approximate) | 2 | 2 | 3 | 3 | 2
| All estimated projects | Included projects
Projects presented & estimated | 4 | 3
Total hours | 5450 | 4500
Total work months | 40.5506 | 33.4821
Total heads needed for period | 13.5169 | 11.1607
Heads on hand (approximate) | 12 | 12
Hours available from heads on hand | 4838.4 | 4838.4
Assumptions:
Estimating Code Values
| Code | Work Hrs
| 1 | 50
| 2 | 100
| 3 | 250
| 4 | 500
| 5 | 750
Other Assumptions:
| Productivity % | 80%
| Work hrs/mo | 134.4
| Months/period | 3