## Instructions
Introduction
This tool allows the IT team to estimate, roughly, the projects and resource allocations for the near-term horizon (focused on 2 months out)
It's intended to be used as an estimating scratchpad, not as a precise day-by-day planner
Prerequisites
You must have the Analysis ToolPak enabled in Excel, since the functions NETWORKDAYS() and EOMONTH() come from there.
Choose Tools/Add-Ins, and check Analysis ToolPak. You'll only have to do this once.
Make sure that you have your security levels set to prompt you for use of macros.
(Choose Tools/Options/Security/Macro Security: Medium; exit Excel and reopen document)
Steps
1) Make a fresh copy of the workbook template for each month you begin planning
2) Most of your work will be done on the Planner tab, but you need to enter some info in advance
3) Set the date for the start of the period on the Parameters tab. Holidays and weekends color in automatically on the Planner
4) Load the titles for all the projects for the month into the Projects tab. Suggestion: keep the ongoing projects the same color from month to month!
5) Allocate each resource to one of the 9 projects, or to vacation or sustainment, for each day, using the project number (1-9) or a "V" or an "S"
6) Resources with planned vacation should have a V put into the appropriate cell for each day they'll be gone
Maintenance
Adding new team members: be sure to keep the Lead as the last one shown on the team in the Planner tab
(i.e., insert new team members before the Lead row)
Also add new team members to the Resources tab first, along with their role and team. Do NOT simply add new resources to the Planner tab!
Holidays must be added on the Holidays tab. The appropriate column on the Planner tab will automatically be colored red when a holiday is added.
Weaknesses/Still To Do
Need to allow more seamless color changing (Planner tab needs to recolorize upon a color change to the project legend)
(Currently does a workaround, in that it recolorizes after every entry)
Background and Technical Approach
Note that leads (as marked in the Resources tab) don't get fully allocated ("counted"). How much they are allocated depends on the parameter setting
(as set in the Parameters tab as "Lead productivity multiplier")
Note that the spreadsheet seems to perform VERY poorly on a Mac (taking a long time to update for each cell entered), but is fine on a PC.
Assumptions
See http://www.peterkretzman.com
Creative Commons License
© Copyright 2005-2013 Peter Kretzman.
No support for this model is implied.
This spreadsheet is licensed under a Creative Commons Attribution 3.0 license.
See http://creativecommons.org/licenses/by/3.0/
This kind of license is also referred to as copyleft.

## Planner
|  | August | [30 empty] | September | [30 empty] | October | [30 empty] | November | [30 empty] | December | [28 empty] | January
 | time axis 2011-08-01 to 2012-01-31
 | time axis 2011-08-01 to 2012-01-31
Applications |  | 2011-08-01: 3
Resource 1 - TBH | bar: 2011-08-01 to 2011-08-06; 2011-08-08 to 2011-08-12; 2011-08-15 to 2011-08-19; 2011-08-22 to 2011-08-26; 2011-08-29 to 2011-09-02
| Resource 2 - Jeff | 2011-08-01: 3; 2011-08-02: 3; 2011-08-03: 3; 2011-08-04: 3; 2011-08-05: 3; 2011-08-08: 3; 2011-08-09: 3; 2011-08-10: 3; 2011-08-11: 3; 2011-08-12: 3; 2011-08-15: 3; 2011-08-16: 3; 2011-08-17: 3; 2011-08-18: 3; 2011-08-19: 3; 2011-08-22: 3; 2011-08-23: 3; 2011-08-24: 3; 2011-08-25: 3; 2011-08-26: 3
| Resource 3 - Mitch | 2011-08-01: 1; 2011-08-02: 1; 2011-08-03: 5; 2011-08-04: 1; 2011-08-05: 1; 2011-08-08: 5; 2011-08-09: 1; 2011-08-10: 5; 2011-08-11: 1; 2011-08-12: 5; 2011-08-15: 1; 2011-08-16: 5; 2011-08-17: 1; 2011-08-18: 5; 2011-08-19: 1; 2011-08-22: 1; 2011-08-23: 1; 2011-08-24: 1; 2011-08-25: 1; 2011-08-26: 1; 2011-08-29: 1; 2011-08-30: 1; 2011-08-31: 1; 2011-09-01: 1; 2011-09-02: 1; 2011-09-06: 1; 2011-09-07: 1; 2011-09-08: 1; 2011-09-12: 1; 2011-09-13: 1; 2011-09-14: 1; 2011-09-15: 1; 2011-09-16: 1
| Resource 4 - Randy | 2011-08-01: 2; 2011-08-02: 2; 2011-08-03: 2; 2011-08-04: 2; 2011-08-05: 2; 2011-08-08: 2; 2011-08-09: 2; 2011-08-10: 2; 2011-08-11: 2; 2011-08-12: 2; 2011-08-15: 2; 2011-08-16: 2; 2011-08-17: 2; 2011-08-18: 2; 2011-08-19: 2; 2011-08-22: 2; 2011-08-23: 2; 2011-08-24: 2; 2011-08-25: 2; 2011-08-26: 2; 2011-08-29: 2; 2011-08-30: 2; 2011-08-31: 2; 2011-09-01: 2; 2011-09-02: 2
| Resource 5 - John | 2011-08-01: 7; 2011-08-02: 7; 2011-08-03: 7; 2011-08-04: 7; 2011-08-05: 7; 2011-08-08: 7; 2011-08-09: 7; 2011-08-10: 7; 2011-08-11: 7; 2011-08-12: 7; 2011-08-15: 7; 2011-08-16: 7; 2011-08-17: 7; 2011-08-18: 7; 2011-08-19: 7; 2011-08-22: 7; 2011-08-23: 7; 2011-08-24: 7; 2011-08-25: 7; 2011-08-26: 7; 2011-08-29: 7; 2011-08-30: 7; 2011-08-31: 7; 2011-09-01: 7; 2011-09-02: 7
| Resource 6 - Larry | 2011-08-01: 2; 2011-08-02: 2; 2011-08-03: N; 2011-08-04: N; 2011-08-05: N; 2011-08-08: 2; 2011-08-09: N; 2011-08-10: N; 2011-08-11: N; 2011-08-12: N; 2011-08-15: 2; 2011-08-16: N; 2011-08-17: N; 2011-08-18: N; 2011-08-19: N; 2011-08-22: 2; 2011-08-23: N; 2011-08-24: N; 2011-08-25: N; 2011-08-26: N; 2011-08-29: 2; 2011-08-30: N; 2011-08-31: N; 2011-09-01: N; 2011-09-02: N
| Resource 7 - Sally | 2011-08-01: N; 2011-08-02: N; 2011-08-03: N; 2011-08-04: N; 2011-08-05: N; 2011-08-08: 2; 2011-08-09: 2; 2011-08-10: N; 2011-08-11: N; 2011-08-12: N; 2011-08-15: 2; 2011-08-16: 2; 2011-08-17: N; 2011-08-18: N; 2011-08-19: N; 2011-08-22: 2; 2011-08-23: 2; 2011-08-24: N; 2011-08-25: N; 2011-08-26: N; 2011-08-29: 2; 2011-08-30: 2; 2011-08-31: N; 2011-09-01: N; 2011-09-02: N
Resource 8 - Jill | bar: 2011-08-01 to 2011-08-06; 2011-08-08 to 2011-08-12; 2011-08-15 to 2011-08-19; 2011-08-22 to 2011-08-26; 2011-08-29 to 2011-09-02
| Manager - Maria | 2011-08-01: 3; 2011-08-02: 4; 2011-08-03: 4; 2011-08-04: 4; 2011-08-05: 4; 2011-08-08: 4; 2011-08-09: 4; 2011-08-10: 4; 2011-08-11: 4; 2011-08-12: 4; 2011-08-15: 4; 2011-08-16: 4; 2011-08-17: 4; 2011-08-18: 4; 2011-08-19: 4; 2011-08-22: V; 2011-08-23: V; 2011-08-24: V; 2011-08-25: V; 2011-08-26: V; 2011-08-29: 4; 2011-08-30: 4; 2011-08-31: 4; 2011-09-01: 4; 2011-09-02: 4
Sustainment Engineering | bar: 2011-08-06 to 2011-08-07
Resource 1 - | bar: 2011-08-06 to 2011-08-07
| Resource 2 - Betty | 2011-08-01: 1; 2011-08-02: 1; 2011-08-03: 2; 2011-08-04: 2; 2011-08-05: 2; 2011-08-08: 2; 2011-08-09: 2; 2011-08-10: 2; 2011-08-11: 2; 2011-08-12: 2; 2011-08-15: 2; 2011-08-16: 2; 2011-08-17: 2; 2011-08-18: 2; 2011-08-19: 2; 2011-08-22: 2; 2011-08-23: 2; 2011-08-24: 2; 2011-08-25: 2; 2011-08-26: 2; 2011-08-29: 2; 2011-08-30: 2; 2011-08-31: 2; 2011-09-01: V; 2011-09-02: V
Resource 3 - Denny | bar: 2011-08-01 to 2011-08-12; 2011-08-14 to 2011-08-19; 2011-08-22 to 2011-08-26; 2011-08-29 to 2011-09-02
Resource 4 - Karen | bar: 2011-08-01 to 2011-08-12; 2011-08-14 to 2011-08-19; 2011-08-22 to 2011-08-26; 2011-08-29 to 2011-09-02; 2011-09-06 to 2011-09-07
Lead | bar: 2011-08-06 to 2011-08-07
Quality Assurance | bar: 2011-08-06 to 2011-08-07
| Resource 2 - Julia | 2011-08-01: N; 2011-08-02: N; 2011-08-03: 2; 2011-08-04: 2; 2011-08-05: 2; 2011-08-08: 2; 2011-08-09: 3; 2011-08-10: 2; 2011-08-11: 3; 2011-08-12: 2; 2011-08-15: 2; 2011-08-16: 2; 2011-08-17: 2; 2011-08-18: 2; 2011-08-19: 2; 2011-08-22: 2; 2011-08-23: 3; 2011-08-24: 2; 2011-08-25: 2; 2011-08-26: 2; 2011-08-29: 2; 2011-08-30: 2; 2011-08-31: 2; 2011-09-01: 2; 2011-09-02: 2
Resource 3 - Glenn | bar: 2011-08-01 to 2011-08-12; 2011-08-15 to 2011-08-19; 2011-08-22 to 2011-08-26; 2011-08-29 to 2011-09-02
| Resource 4 - Zoey | 2011-08-01: N; 2011-08-02: N; 2011-08-03: 2; 2011-08-04: 2; 2011-08-05: 2; 2011-08-08: 2; 2011-08-09: 2; 2011-08-10: 2; 2011-08-11: 2; 2011-08-12: 2; 2011-08-15: 2; 2011-08-16: 2; 2011-08-17: 2; 2011-08-18: 2; 2011-08-19: 2; 2011-08-22: V; 2011-08-23: V; 2011-08-24: V; 2011-08-25: 2; 2011-08-26: 2; 2011-08-29: 2; 2011-08-30: 2; 2011-08-31: 2; 2011-09-01: 2; 2011-09-02: 2
Lead--TBD | bar: 2011-08-06 to 2011-08-07
238 | budgetable workdays for month of August, 2011 | 2011-08-22: Allocated for
[18 empty] | Ratio, | [5 empty] | Month |  |  | %
Workday Project Summary for August |  | 2011-08-09: Proposed Launch Date; 2011-08-17: Dev/QA; 2011-08-23: 2011-08-01; 2011-08-26: 98.7395
1 | 40 | 2011-08-01: Website 3.0; 2011-08-09: January 31, 2012; 2011-08-17: 1.2609; 2011-08-23: 2011-09-01; 2011-08-26: 9.1803
2 | 94 | 2011-08-01: Deferred Revenue; 2011-08-09: February 2, 2012; 2011-08-17: 1.5; 2011-08-23: 2011-10-01; 2011-08-26: 0
3 | 23 | 2011-08-01: Website Performance; 2011-08-09: TBD; 2011-08-17: 6.6667; 2011-08-23: 2011-11-01; 2011-08-26: 0
4 | 0 | 2011-08-01: CRM; 2011-08-09: TBD; 2011-08-17: 0; 2011-08-23: 2011-12-01; 2011-08-26: 0
5 | 6 | 2011-08-01: Sunset App X; 2011-08-09: January 17, 2012; 2011-08-17: 0; 2011-08-23: 2012-01-01; 2011-08-26: 0
6 | 0 | 2011-08-01: Data Warehousing; 2011-08-09: TBD; 2011-08-17: 0
7 | 23 | 2011-08-01: Internal get-well; 2011-08-09: TBD; 2011-08-17: 0
8 | 0 | 2011-08-01: Refactor cache; 2011-08-09: TBD; 2011-08-17: 0
9 | 0 | 2011-08-01: Upgrade bug tracking; 2011-08-09: March, 2012; 2011-08-17: 0
V | 3 | 2011-08-01: PTO
S | 23 | 2011-08-01: SUSTAINMENT; 2011-08-17: #N/A
TOTAL: 235 workdays allocated (99%), Overall Dev/QA ratio for August: 2.5
Dev: 149 days, QA: 63 days
V = Vacation
T = Training
N = rolled off or not yet available
S = Sustainment (non-project) work
Note on C32: Peter Kretzman: Project names come from the Projects tab -- do not insert directly!

## Parameters
Parameter | Value | Note
Start date | 2011-08-01 | Changing this resets the spreadsheet, recolorizes the Planner tab, etc.
Planning horizon start | 2011-08-01 | This is a month, but the model allows for planning for two months in advance
Planning horizon end | 2011-08-31
Total workdays, first month | 23 | Calculated; excludes weekends and holidays
Total workdays, second month | 21 | Calculated; excludes weekends and holidays
Lead productivity multiplier | 0% | Portion of a lead's workday spent on project work

## Projects
Number | Name | Points Estimated | Workdays Estimated
1 | Website 3.0
2 | Deferred Revenue
3 | Website Performance
4 | CRM
5 | Sunset App X
6 | Data Warehousing
7 | Internal get-well
8 | Refactor cache
9 | Upgrade bug tracking
V | PTO
S | Sustainment
Bubbling under:
CMS
Localization
Knowledge Base
MAINTENANCE
Note on D1: Peter Kretzman: Should now include QA and Dev time

## Holidays
Date | Holiday | Day of Week
2005-11-23 | Day before Thanksgiving | Wednesday
2005-11-24 | Thanksgiving | Thursday
2005-11-25 | Day after Thanksgiving | Friday
2005-12-16 | Holiday Party | Friday
2005-12-23 | Christmas Prep | Friday
2005-12-25 | Christmas Day | Sunday
2005-12-26 | Day after Christmas | Monday
2006-01-02 | New Years | Monday
2006-01-16 | Martin Luther King Day | Monday
2006-02-09 | Roller Skating Day | Thursday
2006-02-20 | President's Day | Monday
2006-05-29 | Memorial Day | Monday
2006-07-04 | July 4th | Tuesday
2006-09-04 | Labor Day | Monday
2006-11-23 | Thanksgiving | Thursday
2006-11-24 | Thanksgiving | Friday
2006-12-25 | Christmas Day | Monday
2007-01-01 | New Years | Monday
2007-11-22 | Thanksgiving | Thursday
2007-11-23 | Day after Thanksgiving | Friday
2007-12-24 | Day before Christmas | Monday
2007-12-25 | Christmas Day | Tuesday
2008-01-01 | New Years | Tuesday
2008-02-18 | President's Day | Monday
2008-05-26 | Memorial Day | Monday
2008-07-04 | Independence Day | Friday
2008-09-01 | Labor Day | Monday
2008-11-27 | Thanksgiving | Thursday
2008-11-28 | Thanksgiving | Friday
2008-12-24 | Day before Christmas | Wednesday
2008-12-25 | Christmas Day | Thursday
2009-01-01 | New Year's Day | Thursday
2008-05-26 | Memorial Day | Monday
2008-07-04 | Independence Day | Friday
2009-09-07 | Labor Day | Monday
2009-11-26 | Thanksgiving Day | Thursday
2009-11-27 | Day after Thanksgiving | Friday
2009-12-25 | Christmas Day | Friday
2010-01-01 | New Year's Day | Friday
2010-05-31 | Memorial Day | Monday
2010-07-05 | Independence Day | Monday
2010-09-06 | Labor Day | Monday
2010-11-25 | Thanksgiving Day | Thursday
2010-11-26 | Day After Thanksgiving | Friday
2010-12-24 | Day before Christmas | Friday
2010-12-25 | Christmas | Saturday
2010-12-31 | New Year's Eve | Friday
2011-01-01 | New Year's Day | Saturday
2011-05-30 | Memorial Day | Monday
2011-07-04 | Fourth of July | Monday
2011-09-05 | Labor Day | Monday
2011-11-24 | Thanksgiving Day | Thursday
2011-11-25 | Day After Thanksgiving | Friday
2011-12-26 | Christmas | Monday
2011-12-31 | New Year's Eve | Saturday
2012-01-02 | New Year's Day | Monday
2012-05-28 | Memorial Day | Monday
2012-07-04 | Fourth of July | Wednesday
2012-09-03 | Labor Day | Monday
2012-11-22 | Thanksgiving Day | Thursday
2012-11-23 | Day After Thanksgiving | Friday
2012-12-25 | Christmas | Tuesday
2013-01-01 | New Year's Day | Tuesday

## Resources
Name | Team | Role | Workdays budgetable, August | Workdays budgetable, September
TBH | Applications |  | 23 | 21
Jeff | Applications |  | 23 | 21
Mitch | Applications |  | 23 | 21
Randy | Applications |  | 23 | 21
John | Applications |  | 23 | 21
Larry | Applications |  | 23 | 21
Sally | Applications |  | 23 | 21
Jill | Applications |  | 23 | 21
Maria | Applications | Lead | 0 | 0
Robert | Sustainment |  | 23 | 21
Betty | Sustainment |  | 23 | 21
Denny | Sustainment |  | 23 | 21
Karen | Sustainment |  | 23 | 21
| Sustainment | Lead | 0 | 0
Julia | Quality Assurance |  | 23 | 21
Glenn | Quality Assurance |  | 23 | 21
Zoey | Quality Assurance |  | 23 | 20
TBH | Quality Assurance | Lead | 0 | 0
Total Strategic Resources By Team
Applications | 9
Sustainment | 5
Quality Assurance | 4
Leads | 3
Total available resources: | 15
Workdays budgetable, 1st month, all | 345
Workdays budgetable, 2nd month, all | 314
Workdays budgetable, 1st month, Dev | 276 |  | Budgetable Ratio, Dev/QA: 4
Workdays budgetable, 2nd month, Dev | 252
Workdays budgetable, 1st month, QA | 69
Workdays budgetable, 2nd month, QA | 62

## Allocation summary
Based on allocations made on the Planner tab:
Month | Workdays | Resource Days | Days allocated | % allocated
2011-08-01 | 23 | 238 | 235 | 98.7395
2011-09-01 | 21 | 305 | 28 | 9.1803
2011-10-01 | 21 | 315 | 0 | 0
2011-11-01 | 20 | 300 | 0 | 0
2011-12-01 | 21 | 315 | 0 | 0
2012-01-01 | 21 | 315 | 0 | 0
158
Formulas:
Month = EOMONTH([Month, row above],0)+1
Workdays = NETWORKDAYS(DATE(YEAR([Month]),MONTH([Month]),1),EOMONTH([Month],0),Holidays)
Resource Days = Total_available_resources*[Workdays]-COUNTIF(OFFSET(Planner!C$6,0,[Month]-A3,Total_available_resources+Leads*2,EOMONTH([Month],0)-[Month]+1),"N")
Days allocated = COUNTA(OFFSET(Planner!C$6,0,[Month]-A3,Total_available_resources+Leads*2,EOMONTH([Month],0)-[Month]+1))-COUNTIF(OFFSET(Planner!C$6,0,[Month]-A3,Total_available_resources+Leads*2,EOMONTH([Month],0)-[Month]+1),"N")

## Project Summary
Based on allocations made on the Planner tab:
Monthly Project Workday Summary for August
| Applications main | Applications lead | Sustainment main | Sustainment lead | QA main | QA lead | TOTAL Allocated Days
1 | 17 | 0 | 2 | 0 | 21 | 0 | 40
2 | 37 | 0 | 21 | 0 | 36 | 0 | 94
3 | 20 | 0 | 0 | 0 | 3 | 0 | 23
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 6 | 0 | 0 | 0 | 0 | 0 | 6
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 23 | 0 | 0 | 0 | 0 | 0 | 23
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V | 0 | 0 | 0 | 0 | 3 | 0 | 3
S | 0 | 0 | 23 | 0 | 0 | 0 | 23
TOTAL: 212 workdays allocated (89%)
Monthly Project Workday Summary for September
| Applications main | Applications lead | Sustainment main | Sustainment lead | QA main | QA lead | TOTAL Allocated Days
1 | 10 | 0 | 0 | 0 | 2 | 0 | 12
2 | 2 | 0 | 0 | 0 | 4 | 0 | 6
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 2 | 0 | 0 | 0 | 0 | 0 | 2
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V | 0 | 0 | 2 | 0 | 0 | 0 | 2
S | 0 | 0 | 4 | 0 | 0 | 0 | 4
TOTAL: 26 workdays allocated (8%)
Total Project Workday Summary for August and September
| Project |  | GRAND TOTAL Allocated | Originally Estimated Total | Total Ratio, Dev to QA | August Ratio, Dev to QA | September Ratio, Dev to QA
1 | Website 3.0 |  | 52 | 0 | 1.2609 | 0.90476 | 5
2 | Deferred Revenue |  | 100 | 0 | 1.5 | 1.6111 | 0.5
3 | Website Performance |  | 23 | 0 | 6.6667 | 6.6667 | 0
4 | CRM |  | 0 | 0 | 0 | 0 | 0
5 | Sunset App X |  | 6 | 0 | 0 | 0 | 0
6 | Data Warehousing |  | 0 | 0 | 0 | 0 | 0
7 | Internal get-well |  | 25 | 0 | 0 | 0 | 0
8 | Refactor cache |  | 0 | 0 | 0 | 0 | 0
9 | Upgrade bug tracking |  | 0 | 0 | 0 | 0 | 0
V | PTO |  | 5 | 0 | 0.66667 | 0 | 0
S | Sustainment |  | 27 | 0 | 0 | 0 | 0
Grand Total: |  |  | 238 |  | 2.5303 | 2.4833 | 3